## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US1 | Set up project environment: install dependencies (Flask, SQLite, CoinGecko SDK), initialise SQLite database with required tables (prices, portfolio, risk, predictions, mix_results) | MUST HAVE | — | Group-1 | 3- Completed
1 | 1 | US2 | Configure watchlist of 8 coins in config.py (BTC, ETH, BNB, SOL, ADA, XRP, MATIC, LINK) and connect to CoinGecko /coins/markets API to fetch live prices and store in DB | MUST HAVE | — | Group-1 | 3- Completed
1 | 1 | US3 | Apply parallel execution using ThreadPoolExecutor to bulk-fetch live prices for all watchlist coins simultaneously and store snapshots in DB | SHOULD HAVE | US2 | Group-1 | 3- Completed
1 | 1 | US4 | Fetch and display CoinGecko trending coins; learn datetime module, NumPy operations, and pandas for data handling | SHOULD HAVE | — | Group-1 | 3- Completed
2 | 2 | US5 | Load price history from DB, compute percentage returns per coin, run 1000 random weight iterations (Monte Carlo) to find best Sharpe ratio, best return, and lowest risk portfolio mixes | MUST HAVE | US2 | Group-1 | 3- Completed
2 | 2 | US6 | Save winning mix results (weights, expected return, risk) to mix_results table in SQLite; fetch and display stored mixes | SHOULD HAVE | US5 | Group-1 | 3- Completed
2 | 2 | US7 | Run the three mix strategies (best Sharpe, best return, lowest risk) in parallel using ThreadPoolExecutor and save all outputs to DB | SHOULD HAVE | — | Group-1 | 3- Completed
2 | 2 | US8 | Compare portfolio mix returns vs individual single-asset returns; plot line graphs; export results to CSV in reports/ folder | MUST HAVE | US5 | Group-1 | 3- Completed
2 | 2 | US9 | Prepare a .md documentation file summarising milestone 2 work: mix calculator logic, results, and insights | SHOULD HAVE | — | Group-1 | 3- Completed
3 | 3 | US10 | Implement 6 risk rules per coin (volatility tier LOW/MEDIUM/HIGH, Sharpe ratio, max drawdown, mean return, momentum trend, MA signal); run checks in parallel; store results in risk_snapshots table; send email alert via SMTP/Resend when any coin breaches threshold | MUST HAVE | US2 | Group-1 | 3- Completed
3 | 3 | US11 | Predict next-period price for each coin using linear regression (slope + intercept over price history) and moving average crossover; run predictions in parallel; save to predictions table; export CSV reports | MUST HAVE | US2 | Group-1 | 3- Completed
4 | 4 | US12 | Implement portfolio spreading rules: max 40% / min 5% per coin allocation; drift detector with 10pp rebalance threshold; show BUY/SELL/HOLD actions; log rebalance events to DB | MUST HAVE | US5 | Group-1 | 3- Completed
4 | 4 | US13 | Run MA-crossover backtesting strategy (golden cross BUY / death cross SELL) on historical price data; calculate total return, win rate, max drawdown per coin; display trade log and summary; stress test portfolio under bull (+30%), bear (-40%), flash crash (-20%) scenarios | MUST HAVE | US12 | Group-1 | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 40 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | 1 | Read project requirements, install Flask, SQLite3, CoinGecko API library; set up virtual environment and requirements.txt | 2026-02-02 | 2026-02-02 | Group-1 | Build | 3- Completed | 1 | bar: Day 1
US1 | 2 | Design and initialise SQLite database schema: create prices, portfolio, mix_results, risk_snapshots, predictions, alerts, rebalance_log tables | 2026-02-03 | 2026-02-03 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US1 | 3 | Implement database.py: init_db(), save_price(), get_history(), get_prices() functions with CoinGecko API integration | 2026-02-04 | 2026-02-05 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US2 | 4 | Configure config.py: define WATCHLIST (8 coins), API settings, CoinGecko endpoints, and all module configs (MIX, RISK, PREDICTION, SPREAD) | 2026-02-05 | 2026-02-06 | Group-1 | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US2 | 5 | Implement milestone1_setup.py: task_init_database(), task_show_watchlist(), task_parallel_fetch() — bulk fetch live prices for all 8 coins and store in DB | 2026-02-09 | 2026-02-10 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US3 | 6 | Apply ThreadPoolExecutor parallel fetch — run simultaneous price fetch for all watchlist coins; validate data stored correctly in DB | 2026-02-10 | 2026-02-11 | Group-1 | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US4 | 7 | Implement task_trending() to fetch CoinGecko trending coins; explore NumPy operations on price arrays; learn pandas date handling | 2026-02-12 | 2026-02-12 | Group-1 | Build | 3- Completed | 1 | bar: Day 1
US4 | 8 | Sprint 1 review — validate all DB tables populated, test CLI menu in main.py, fix issues identified in sprint evaluation | 2026-02-13 | 2026-02-13 | Group-1 | Unit Test | 3- Completed | 1 | bar: Day 1
SPRINT 2 BACKLOG
US5 | 1 | Implement task_load_returns(): load price history from DB, compute percentage returns per coin using _pct_returns() | 2026-02-16 | 2026-02-16 | Group-1 | Coding | 3- Completed | 1 | bar: Day 1
US5 | 2 | Implement task_run_mixes(): run 1000 Monte Carlo random weight iterations using _random_weights(); compute portfolio return, risk, Sharpe ratio with _portfolio_stats() | 2026-02-17 | 2026-02-18 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US5 | 3 | Implement task_show_and_save(): display winning mixes (best Sharpe, best return, lowest risk) with coin weights; save results to mix_results table | 2026-02-19 | 2026-02-19 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US6 | 4 | Implement database functions: save_mix(), get_mix_history(); verify mix data stored and fetchable from DB | 2026-02-20 | 2026-02-20 | Group-1 | Coding | 3- Completed | 1 | bar: Day 1
US7 | 5 | Extend mix calculation to run all three strategies (best Sharpe, best return, lowest risk) in parallel using ThreadPoolExecutor; save all outputs to DB | 2026-02-23 | 2026-02-23 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US8 | 6 | Compare portfolio mix returns vs individual single-asset returns; plot line graphs using matplotlib; draw insights on diversification benefit | 2026-02-24 | 2026-02-25 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US8 | 7 | Export comparison results to CSV in reports/ folder; validate CSV output format | 2026-02-25 | 2026-02-25 | Group-1 | Coding | 3- Completed | 1 | bar: Day 1
US9 | 8 | Sprint 2 evaluation and write milestone2.md documentation: describe mix calculator logic, Monte Carlo approach, results and key insights | 2026-02-27 | 2026-02-27 | Group-1 | Others | 3- Completed | 1 | bar: Day 1
SPRINT 3 BACKLOG
US10 | 1 | Implement coin_risk(): calculate volatility (pstdev), mean return, Sharpe ratio, max drawdown per coin; classify risk tier (LOW/MEDIUM/HIGH) using config.RISK thresholds | 2026-03-02 | 2026-03-03 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US10 | 2 | Implement task_parallel_risk(): run coin_risk() for all 8 watchlist coins concurrently using ThreadPoolExecutor (4 workers); store results in risk_snapshots table | 2026-03-04 | 2026-03-04 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US10 | 3 | Implement task_check_alerts(): detect coins with 24h price change >= alert_threshold; save alerts to DB; implement task_send_email() via SMTP (Gmail) / Resend API | 2026-03-05 | 2026-03-06 | Group-1 | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US11 | 4 | Implement predict_coin(): _linear_regression() for slope/intercept on price history; _moving_average() for short (5) and long (15) window MA; _momentum_trend() and _ma_signal() for BUY/SELL/HOLD | 2026-03-09 | 2026-03-11 | Group-1 | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 1; Day 3: 1
US11 | 5 | Implement task_run_predictions(): run predict_coin() in parallel for all coins; save predictions to DB; implement task_export_csv() to export prices, risk, predictions and alerts as timestamped CSV files | 2026-03-12 | 2026-03-13 | Group-1 | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
SPRINT 4 BACKLOG
US12 | 1 | Implement task_show_portfolio(): display current holdings with live prices, value, allocation %, P&L%; implement task_enforce_rules(): flag coins exceeding max 40% or below min 5% allocation using config.SPREAD | 2026-03-16 | 2026-03-17 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US12 | 2 | Implement task_rebalance(): detect allocation drift > 10pp vs equal-weight target; output BUY/SELL/HOLD actions; log rebalance events to rebalance_log table in DB | 2026-03-18 | 2026-03-18 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US13 | 3 | Implement backtest_coin(): MA crossover strategy — golden cross (short MA > long MA) = BUY, death cross = SELL; track cash, holdings, equity curve, max drawdown, win rate per coin | 2026-03-19 | 2026-03-20 | Group-1 | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US13 | 4 | Implement task_stress_test(): simulate portfolio value under 3 market scenarios (bull +30%, bear -40%, flash crash -20%) using config.SPREAD['stress_scenarios']; display P&L for each scenario | 2026-03-20 | 2026-03-20 | Group-1 | Coding | 3- Completed | 2 | Day 1: 2
US13 | 5 | Full system integration test: run main.py end-to-end across all milestones; fix bugs; prepare demo walkthrough for presentation | 2026-03-23 | 2026-03-24 | Group-1 | Unit Test | 3- Completed | 2 | bar: Day 1 to Day 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2nd Feb | Understanding project structure, setting up virtual environment and installing dependencies (Flask, SQLite3, requests, python-dotenv) | Created requirements.txt; virtual environment set up successfully; all packages installed
1 | 3rd Feb | Designing SQLite database schema — understanding what tables are needed (prices, portfolio, mix_results, risk_snapshots, predictions, alerts, rebalance_log) | Database schema designed and init_db() implemented in database.py; all 7 tables created successfully
1 | 4th Feb | Connecting to CoinGecko /coins/markets API — understanding query params (vs_currency, ids, order) and handling rate limits | get_prices() implemented; successfully fetched live prices for all 8 watchlist coins; data stored in prices table
1 | 5th Feb | Configuring config.py with all module settings — API keys, WATCHLIST, MIX, RISK, PREDICTION, SPREAD parameters | config.py complete with all settings loaded from .env; WATCHLIST of 8 coins (BTC, ETH, BNB, SOL, ADA, XRP, MATIC, LINK) configured
1 | 6th Feb | Implementing milestone1_setup.py — task_init_database() and task_show_watchlist() tasks | Both tasks working; database initialised; watchlist displaying correctly with API URL and rate-limit settings
1 | 9th Feb | Implementing parallel fetch using ThreadPoolExecutor — understanding concurrent.futures module | task_parallel_fetch() implemented; all 8 coins fetched simultaneously; 24h change and price stored correctly in DB
1 | 10th Feb | Implementing task_trending() for CoinGecko trending coins; exploring NumPy array operations on price data | Trending coins displayed; NumPy mean, pstdev operations tested on price arrays; pandas date handling explored
1 | 11th Feb | Milestone 1 class timing evaluation (5:30–6:30 PM) | Feedback taken; fixed edge case in save_price() when price_change_percentage_24h is None; DB validated with all 8 coins stored
1 | 12th Feb | Sprint 1 evaluation — validating all tables, testing CLI main.py menu | All DB tables populated correctly; main.py menu tested end-to-end; minor formatting fixes applied
1 | 13th Feb | Sprint 1 retrospection and introduction to Milestone 2 — Investment Mix Calculator concepts | Understood Monte Carlo random weight approach; risk_free_rate and Sharpe ratio formula explained; Sprint 2 plan ready
2 | 16th Feb | Loading price history from DB and computing percentage returns — understanding _pct_returns() logic | task_load_returns() implemented; percentage returns computed for all 8 coins; minimum history validation added
2 | 17th Feb | Implementing Monte Carlo random weight generation using _random_weights() with minimum weight constraint | _random_weights() working with min_weight=0.05; uniform constraint validated; 1000 iterations running correctly
2 | 18th Feb | Implementing _portfolio_stats() to calculate portfolio return, risk (pstdev) and Sharpe ratio for each weight combination | _portfolio_stats() correct; Sharpe ratio formula verified; best_sharpe, best_return, lowest_risk tracking implemented
2 | 19th Feb | Implementing task_show_and_save(): display and save winning mix results — best Sharpe, best return, lowest risk portfolios | save_mix() in database.py implemented; winning mixes displaying with coin weights and stats; stored in mix_results table
2 | 20th Feb | Running all three mix strategies in parallel using ThreadPoolExecutor; ensuring thread-safe DB writes | Parallel mix execution working; all 3 strategies running concurrently; DB writes validated with no race conditions
2 | 23rd Feb | Comparing portfolio mix return vs individual single-asset returns; plotting line graphs with matplotlib | Comparison logic implemented; line graph plotted for portfolio vs 8 individual coins; diversification benefit visible
2 | 24th Feb | Milestone 2 evaluation (5:30–6:30 PM) — feedback on graph clarity and export format | Feedback: plot only 30 data points for clarity; CSV export column names standardised; applied improvements
2 | 25th Feb | Exporting results to timestamped CSV in reports/ folder; writing milestone2.md documentation | CSV export working for mix results and comparison data; milestone2.md drafted with logic explanation and insights
2 | 27th Feb | Sprint 2 evaluation and retrospection — review of all milestone 2 tasks | All Sprint 2 tasks verified complete; Sprint 3 plan discussed — risk checker rules and prediction engine
3 | 2nd Mar | Understanding 6 risk metrics: volatility, mean return, Sharpe ratio, max drawdown, momentum trend, MA signal — and thresholds in config.RISK | coin_risk() skeleton implemented; volatility (pstdev) and mean return computed; LOW/MEDIUM/HIGH tier logic added
3 | 3rd Mar | Implementing full coin_risk(): Sharpe ratio (mean_ret/vol), max drawdown calculation, risk tier classification | coin_risk() complete; all 6 metrics computed correctly; results validated against manual calculations for BTC and ETH
3 | 4th Mar | Running risk checks in parallel using ThreadPoolExecutor (4 workers); storing results in risk_snapshots table | task_parallel_risk() complete; 4 concurrent workers processing 8 coins; risk snapshots saved and queryable in DB
3 | 5th Mar | Implementing price alert detection — checking 24h change against alert_threshold; saving alerts to alerts table | task_check_alerts() implemented; alert threshold 0.1% tested; database.save_alert() storing direction and message correctly
3 | 6th Mar | Implementing email alert via SMTP (Gmail) — MIMEText, starttls, SMTP login; testing with EMAIL_ENABLED flag | Email sending working via Gmail SMTP; Resend API option also implemented; tested with mock alert data; .env config validated
3 | 9th Mar | Implementing _linear_regression() from scratch — slope and intercept formula on price history array | Linear regression slope and intercept computed correctly; verified against scipy for 3 coins; linreg_forecast for 5 periods working
3 | 10th Mar | Implementing _moving_average(), _momentum_trend(), _ma_signal() — BUY/SELL/HOLD signal generation logic | All 3 functions working; short MA (5) and long MA (15) windows tested; BULLISH/BEARISH/NEUTRAL trend correct on sample data
3 | 11th Mar | Milestone 3 evaluation (5:30–6:30 PM) — feedback on prediction accuracy and parallel execution | Feedback: improve confidence_band calculation; fix edge case for coins with < 15 price snapshots; applied fixes
3 | 12th Mar | Implementing task_run_predictions() in parallel; task_export_csv() generating timestamped CSV files for prices, risk, predictions, alerts | Parallel prediction working for all 8 coins; 4 CSV files generated correctly in reports/; file naming validated
3 | 13th Mar | Sprint 3 evaluation and retrospection — review risk checker and predictor; Sprint 4 plan for spreading rules and backtesting | All Sprint 3 tasks complete; spreading rules design discussed — max/min alloc, drift threshold, rebalance logic, stress scenarios
4 | 16th Mar | Implementing task_show_portfolio(): display holdings with live prices, value, allocation % and P&L%; add demo positions if portfolio is empty | task_show_portfolio() complete; P&L calculation correct; _current_alloc() computing percentages correctly from live prices
4 | 17th Mar | Implementing task_enforce_rules(): flag coins exceeding max 40% or below min 5% allocation; generating REDUCE/INCREASE messages | task_enforce_rules() working with config.SPREAD thresholds; demo portfolio tested with all 3 scenarios (OK, over-allocated, under-allocated)
4 | 18th Mar | Implementing task_rebalance(): drift detection vs equal-weight target; BUY/SELL/HOLD actions; log_rebalance() saving to rebalance_log table | Drift detector working with 10pp threshold; rebalance actions logged to DB; equal-weight target for 8 coins (12.5% each) validated
4 | 19th Mar | Implementing backtest_coin(): MA crossover strategy — golden cross BUY signal, death cross SELL signal; tracking cash, holdings, equity curve | backtest_coin() complete; golden cross and death cross logic verified on BTC history; equity curve, max drawdown, win rate computed
4 | 20th Mar | Implementing task_stress_test(): simulate portfolio under bull (+30%), bear (-40%), flash crash (-20%) scenarios; display P&L for each | Stress test working; 3 scenarios from config.SPREAD['stress_scenarios'] applied; P&L in $ and % displayed correctly
4 | 23rd Mar | Full end-to-end integration test: run main.py across all 4 milestones; fix bugs; prepare demo walkthrough | All milestones running cleanly in sequence; minor edge case fixed in milestone2 when DB has only 1 coin history; demo script prepared
4 | 25th Mar | Demo Presentation (5:30–6:30 PM) — full project demonstration to evaluators | All 4 milestones demonstrated live; CoinGecko API, mix calculator, risk checker, predictor, spreading rules and backtest all presented
4 | 27th Mar | Mock Presentation (5:30–6:30 PM) — final rehearsal | Presentation refined; focused on explaining project outcomes clearly without overloading on code; terminal demo polished

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-14 | Group-1 | Use CoinGecko bulk /coins/markets endpoint instead of per-coin calls to avoid rate limit | — | Continue with parallel fetch and DB storage approach | Switched to bulk API call in get_prices(); rate-limit gap set to 2s in config; all 8 coins fetching cleanly
2 | Sprint 1 | 2026-02-02 | 2026-02-14 | Group-1 | Handle None values for price_change_percentage_24h before saving to DB | Skipping null checks in save_price() | Continue validating all API fields before DB insert | Added null-safe handling in save_price(); DB inserts no longer fail on missing 24h change data
3 | Sprint 2 | 2026-02-16 | 2026-02-27 | Group-1 | Use minimum 2 coins with price history before running mix calculator | — | Continue Monte Carlo random weight approach with 1000 iterations | Added validation in task_run_mixes() to check len(returns) >= 2 before proceeding
4 | Sprint 2 | 2026-02-16 | 2026-02-27 | Group-1 | Cap portfolio graph to 30 data points for clearer visualisation | Plotting all data points making chart unreadable | Continue comparing portfolio vs individual asset returns | Updated plot to show last 30 snapshots; insights now clearly visible on the chart
5 | Sprint 2 | 2026-02-16 | 2026-02-27 | Group-1 | Standardise CSV export column names and add timestamp to filenames | Inconsistent column naming in exported CSV files | Continue exporting reports to reports/ folder | CSV columns standardised; timestamp suffix (YYYYMMDD_HHMMSS) added to all export filenames
6 | Sprint 3 | 2026-03-02 | 2026-03-13 | Group-1 | Fix confidence_band to use residual pstdev instead of raw value; handle coins with insufficient history gracefully | Using raw price pstdev for confidence band — incorrect methodology | Continue parallel risk check with 4 ThreadPoolExecutor workers | Confidence band now computed as ±pstdev of residuals (actual - predicted); edge case guard added for < 15 snapshots
7 | Sprint 3 | 2026-03-02 | 2026-03-13 | Group-1 | Ensure EMAIL_ENABLED flag in .env is documented clearly in README for evaluators | Email alerts silently failing when .env not configured | Continue using both SMTP (Gmail) and Resend API options for email alerts | README updated with EMAIL_ENABLED=true setup steps; .env.example added to repo
8 | Sprint 4 | 2026-03-16 | 2026-03-25 | Group-1 | Use _add_demo_positions() to populate portfolio before spreading rule tests when portfolio is empty | Running spreading rules on empty portfolio causing division errors | Continue using equal-weight target (100/n per coin) for rebalance drift detection | Demo positions added in run() before task_show_portfolio(); portfolio never empty during evaluation
9 | Sprint 4 | 2026-03-16 | 2026-03-25 | Group-1 | Add milestone2 edge-case fix: skip mix calculation if only 1 coin has enough history | — | Continue backtesting with MA crossover strategy (short=5, long=15) | Guard added in run_milestone2() in main.py to check len(returns) < 2 and print clear message